**Sample Evaluation Timeline**

| **Month**  | **Project Goal**  | **Related Objective**  | **Activity**  | **Expected Completion Date**  | **Person Responsible**  |
| --- | --- | --- | --- | --- | --- |
| 1-12  | Continue to conduct process evaluation in Florida of APYA/STREET Smart programs.  | Monitor the operations of APYA/STREET Smart programs. | Conduct site visits to review and discuss program operations.  | October 2005 April 2006  | Bob SmithTim Black  |
| 1-12  | Continue to conduct outcome evaluation.  | Complete data collection for experimental group. | Work with Community Specialists to complete STREET Smart exit data for experimental group.  | May 2006  | Community Specialists/Tim Matthews  |
| Finalize data collection procedures for control group.  | Extract and analyze JJIS data on demographics and service/placement history.  | December 2006  | NCCD Research Team  |
| Access and analyze information sources for follow-up data collection on outcome measures for experimental and control groups  | Receive second annual data extract from DJJ for conducting recidivism analysis.  | December 2006  | Bob Smith  |
| Receive second annual employment and education data extract from FETPIP.  | February 2007  | Bob SmithTim Black  |
| Receive second annual educational outcome data extract from DOE  | April 2007  | Bob SmithTim Blacks  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Month**  | **Project Goal**  | **Related Objective**  | **Activity**  | **Expected Completion Date**  | **Person Responsible**  |
|  |  | Conduct sample case tracking and follow-up interviewing.  | Initiate and complete tracking and follow-up component of the evaluation for 710 cases.  | September 2007  | Subcontractor  |
| Develop and implement initial plans for data analysis and reporting.  | Conduct analysis of FETPIP data.  | April 2007  | NCCD Research Team  |
| Conduct analysis using DOE/EDW data. | June 2007  | NCCD Research Team  |
| Conduct analysis and reporting for recidivism using DJJ data extract.  | February 2007  | NCCD Research Team  |
| Maintain privacy and protection of human subjects’ certifications  | Complete all privacy and certifications as required.  | Ongoing  | Bob Smith |